## Risk Register
Information Security Risk Register: Sample (Fictional Company: Northwind Health Tech, Cloud SaaS)
Sample for portfolio use. All data is fictional. Blue = input, black = formula. Scales and thresholds are on the 'Scoring Criteria' tab.
© 2026 Hina Qurashee. All rights reserved.
Risk ID | Risk Description (If / Then / Resulting in) | Category | Affected Asset / Process | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Control Reference (ISO 27001:2022 / NIST CSF) | Treatment | Mitigation Actions | Risk Owner | Due Date | Status | Residual Likelihood | Residual Impact | Residual Score | Residual Rating
R-001 | If privileged accounts lack MFA, then credential theft could allow database access, resulting in a PHI breach, HIPAA penalties and loss of customers. | Cybersecurity | Customer PHI database | 3 | 5 | 15 | High | A.5.17, A.8.5 / PR.AA | Mitigate | Enforce phishing-resistant MFA on all admin accounts; quarterly privileged access review. | CISO | 2026-11-30 | In Progress | 2 | 5 | 10 | Medium
R-002 | If vendors are not assessed before onboarding, then weak vendor controls could expose shared data, resulting in a reportable incident and contract liability. | Third-Party | Payment and analytics vendors | 4 | 4 | 16 | High | A.5.19, A.5.22 / GV.SC | Mitigate | Implement tiered vendor due diligence (questionnaire, SOC 2 review) and annual reassessment. | Vendor Risk Manager | 2026-12-15 | Open | 3 | 3 | 9 | Medium
R-003 | If backups are not tested, then restoration could fail after ransomware or outage, resulting in extended downtime and SLA breach. | Operational | Production cloud environment | 3 | 5 | 15 | High | A.8.13, A.5.30 / PR.DS, RC.RP | Mitigate | Run quarterly restore tests; keep immutable offsite backups; document RTO/RPO. | IT Operations Manager | 2026-11-15 | In Progress | 2 | 4 | 8 | Medium
R-004 | If the annual risk assessment and policy review lapse, then audit gaps could go unnoticed, resulting in findings and fines from regulators. | Compliance | HIPAA Security Rule program | 3 | 4 | 12 | High | A.5.36, A.5.1 / GV.PO | Mitigate | Set annual compliance calendar; assign policy owners; track attestations in GRC tool. | Compliance Manager | 2026-10-31 | Open | 2 | 3 | 6 | Medium
R-005 | If staff are not trained on phishing, then a malicious link could be clicked, resulting in malware infection and lateral movement. | Cybersecurity | Employee workstations and email | 4 | 3 | 12 | High | A.6.3, A.8.7 / PR.AT | Mitigate | Monthly phishing simulations; role-based training; email filtering upgrade. | Security Awareness Lead | 2026-12-31 | In Progress | 3 | 2 | 6 | Medium
R-006 | If patches are not applied within SLA, then known vulnerabilities could be exploited, resulting in service compromise or data loss. | Cybersecurity | Public-facing web application | 4 | 4 | 16 | High | A.8.8 / ID.RA, PR.PS | Mitigate | Define patch SLAs by severity (critical within 7 days); weekly vulnerability scans; report KPI to leadership. | Head of Engineering | 2026-11-20 | In Progress | 2 | 4 | 8 | Medium
R-007 | If data retention schedules are not enforced, then excess personal data could be held, resulting in a larger breach footprint and GDPR/CCPA exposure. | Privacy | Customer personal data | 3 | 3 | 9 | Medium | A.5.33, A.8.10 / GV.PO | Mitigate | Publish retention schedule; automate deletion jobs; annual data inventory. | Data Protection Officer | 2027-01-31 | Open | 2 | 2 | 4 | Low
R-008 | If there is no tested BCP/DR plan, then a regional outage could stall operations, resulting in prolonged downtime and revenue loss. | Business Continuity | Core platform and support operations | 2 | 5 | 10 | Medium | A.5.29, A.5.30 / RC.RP | Mitigate | Complete business impact analysis; run annual tabletop and failover exercise. | Business Continuity Lead | 2027-02-28 | Open | 1 | 4 | 4 | Low
R-009 | If access is not removed promptly on termination, then former staff could retain access, resulting in data theft or sabotage. | Insider Threat | Source code and customer data | 3 | 4 | 12 | High | A.6.5, A.5.18 / PR.AA | Mitigate | Automate offboarding via HR-IdP integration; monthly access reconciliation. | HR Director / IT Manager | 2026-11-10 | In Progress | 1 | 4 | 4 | Low
R-010 | If the incident response plan is untested, then response to a breach could be slow, resulting in missed 60-day notification deadlines and higher costs. | Cybersecurity | Incident response capability | 3 | 4 | 12 | High | A.5.24, A.5.26 / RS.MA | Mitigate | Update IR plan and playbooks; run semi-annual tabletop; retain external IR firm. | CISO | 2026-12-10 | Open | 2 | 3 | 6 | Medium
R-011 | If an unsupported OS stays in service, then unpatched flaws could be exploited, resulting in compromise of billing data. | Technology | Legacy on-prem billing server | 4 | 3 | 12 | High | A.8.8, A.8.9 / ID.AM | Avoid | Migrate billing workload to supported cloud platform and decommission server. | Head of Engineering | 2027-03-31 | Open | 1 | 3 | 3 | Low
R-012 | If cyber insurance limits are below realistic loss, then a major breach could exceed coverage, resulting in uninsured financial loss. | Financial | Cyber liability coverage | 2 | 4 | 8 | Medium | GV.RM | Transfer | Review coverage limits against breach cost modeling; renew policy with adequate limits. | CFO | 2026-12-31 | Open | 2 | 3 | 6 | Medium
R-013 | If secrets are stored in code repositories, then leaked keys could grant cloud access, resulting in unauthorized resource use or data exposure. | Cybersecurity | Developer tools and CI/CD | 3 | 4 | 12 | High | A.8.4, A.8.24 / PR.DS | Mitigate | Deploy secret scanning in pipelines; move secrets to a vault; rotate exposed keys. | DevSecOps Lead | 2026-11-25 | In Progress | 1 | 4 | 4 | Low
R-014 | If physical access controls are weak, then unauthorized entry could occur, resulting in equipment theft or tampering. | Physical | Office server closet | 2 | 3 | 6 | Medium | A.7.2, A.7.4 / PR.AA | Accept | Accept with existing badge access and CCTV; review access list annually. | Facilities Manager | 2027-06-30 | Accepted | 2 | 3 | 6 | Medium
Assumptions: scores are illustrative judgments for a fictional company; control references map to ISO/IEC 27001:2022 Annex A and NIST CSF 2.0 functions; owners are roles, not named people.

## Scoring Criteria
Scoring Criteria & Risk Appetite
Score = Likelihood x Impact (1-25). Thresholds below drive the Rating column on the Risk Register.
Score | Likelihood | Impact
1 | Rare: <5% chance in 12 months | Negligible: no customer impact, <$10K loss
2 | Unlikely: 5-20% | Minor: limited internal disruption, $10K-$50K
3 | Possible: 20-50% | Moderate: some customer impact, minor regulatory notice, $50K-$250K
4 | Likely: 50-80% | Major: significant outage or data exposure, regulatory action, $250K-$1M
5 | Almost certain: >80% | Severe: large breach, loss of key customers or license, >$1M
Rating Thresholds (editable inputs)
Rating | Minimum Score | Required Action
Critical | 20 | Escalate to executive leadership; treat immediately
High | 12 | Treatment plan required within 30 days; monthly review
Medium | 6 | Treatment plan within 90 days; quarterly review
Low | 1 | Accept and monitor; annual review
Note: scales and thresholds are illustrative assumptions for this sample, loosely modeled on common NIST SP 800-30 / ISO 27005 practice. Blue = editable input.
© 2026 Hina Qurashee. All rights reserved.

## Heat Map
Inherent Risk Heat Map (count of risks)
Counts update automatically from the Risk Register.
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 2 | 2 | 0
3 | 0 | 0 | 1 | 4 | 2
2 | 0 | 0 | 1 | 1 | 1
1 | 0 | 0 | 0 | 0 | 0
Summary by Rating
Rating | Inherent | Residual
Critical | 0 | 0
High | 10 | 0
Medium | 4 | 9
Low | 0 | 5
Total | 14 | 14
Average Score | 11.9286 | 6
© 2026 Hina Qurashee. All rights reserved.